## Sheet1
Step | MAIC | Focus | Action | Question | Know | See | Tool | Data | Location
1 | Measure | CTQ | Select CTQ Characteristic | Does the selected CTQ offer high impact -- quality, cost or time ? | Selection critieria and timeframe | Decision Matrix | Brainstorming, pareto, C&E analysis, process/design FMEA, COPQ, RTY, dpu, Y.norm | Continuous and discrete data, Spec Limits for short term, | Simulator, QA/QC, Manufacturing
2 | Measure | CTQ | Define Performance Standards | Can stated performance standards satisfy customer and business needs? | Mean, target, Spec Limits, functional limits, required capability | Graphical presentation of requirements | Communication with customers, Strat Plan, Design specifications | Reliability and warranty data, engineering data, Mean, Standard Deviation, Spec Limits for short term | Simulator
3 | Measure | CTQ | Validate Measurement System | Is the current measurement system acceptable by conventional standards? | P/T and R&R values | GRR Table | Gage R&R spreadsheet | Sample Data over process range | Lab/Floor
4 | Analyze | CTQ | Establish Product Capability | Does the existing capability of this CTQ need to be improved to meet performance requirements? | Baseline m, s, Cp, Cpk, Pp, Ppk | Minitab Capability Six Pack and Six Sigma Macro Reports | Minitab | n= 500 subgroups = 100 subgroup size = 5, record Y and X's for future use | Simulator
5 | Analyze | CTQ | Define Performance Objectives | Do we know the extent to which the variation must be reduced to meet objectives? | Baseline and target m, s, Cp, Cpk, Pp, Ppk | Picture of "is" and "ought" | Minitab | From capability analysis and performance standards | Previous outputs
6 | Analyze | CTQ | Identify Variation Sources | Do we know the major family of variation? | Inputs, noise variables | Process Map and capabilities of each input variables | Process Map, FMEA, Cause and Effect Matrix, Multivari chart | Process understanding | Grey Matter
7 | Improve | CTQ and CTP (Critical to Process) | Screen Potential Causes | Are the leverage CTP's known? | Direction of effect and sensitivity of selected CTP's with respect to m, s | Graphical and tabular form | Main Effects Plot, ANOVA, e (SSe/SSt), Autocorrelation, Regression | Data from product capability study
8 | Improve | CTQ and CTP (Critical to Process) | Study Key Relationships | Do we know what relationships among the CTP's must be controlled ? | Main effects, Interactions, clear of confounding | Graphical and tabular form | Main Effects Plot,Interaction Plots, ANOVA, e (SSe/SSt), Autocorrelation, Regression
9 | Improve | CTP | Establish Operating Tolerances | Do we know the functional limits for the CTP's? | Regression coefficients and coding information | Equation and graphical | Main effects plots, regression, interactions plot
10 | Control | CTP | Validate Measurement System (for X's) | Is the current measurement systems acceptable by conventional standards for the CTP's? | P/T and R&R values | GRR Table | Gage R&R spreadsheet | Sample Data over process range | Shop floor
11 | Control | CTP | Determine Process Capability (Y and X's) | Can process operate within chosen limits to a 6s capability? | Baseline m, s, Cp, Cpk, Pp, Ppk | Minitab Capability Six Pack and Six Sigma Macro Reports | Minitab | Rational subgroups of continuous data | Shop floor
12 | Control | CTP | Implement Process Control System | Can objectives be consistently met? | Control charts, CTQ yield information | Six Sigma Reports | Six Sigma Macro, control chart option